## Sheet1
GOVERNMENT OF BIHAR DEPARTMENT OF AGRICULTURE MONTHLY PROGRESS REPORT OF AGRICULTURAL TECHNOLOGY MANAGEMENT AGENCY (NATIONAL MISSION ON AGRICULTURAL EXTENSION AND TECHNOLOGY (NMAET)
Format - 1
Monthly Progress Report of ATMA Scheme
| Date of Entry: 31.10.2017 |  | Physical unit : Number/Acre/Others |  |  |  | Amount in Rs. Lakh |  |  | % Achievement (Fin.)
| Reported Month - October 2017 |  | YEAR - 2017-18 |  |  |  | Name of District - Banka
Sl. No. | Activities | Commulative Physical and Financial Report up to Previous month |  |  |  | Progress Report of Persent Month |  | Commulative Physical and Financial Report up to Persent month
|  | Target |  | Achievement |  | Achievement |  | Achievement
|  | P | F | P | F | P | F | P | F
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Farm Oriented Activities
|  | 5 | 1.25
B.1 | Training of Farmer's
B.2 | a) Inter State | 132 | 1.65
No. of Trainings Programmes *
No.of Participants *
No of Male Farmers*
Male (Gen)
Male (OBC)
Male (SC)
Male (ST)
Male (Minorities)
No.of Female Farmers *
Female (Gen)
Female (OBC)
Female (SC)
Female (ST)
Female (Minorities)
Duration of training (in Days) *
| b) Within State | 770 | 7.7 | 19 | 0.31575 |  |  | 30 | 0.31575 | 4
| No. of Trainings Programmes * |  |  | 1 |  |  |  | 2
| No.of Participants * |  |  | 19 |  |  |  | 30
| No of Male Farmers* |  |  | 19 |  |  |  | 29
| Male (Gen) |  |  | 4 |  |  |  | 5
| Male (OBC) |  |  | 13 |  |  |  | 22
| Male (SC) |  |  | 0
| Male (ST) |  |  | 1 |  |  |  | 1
| Male (Minorities) |  |  | 1 |  |  |  | 1
| No.of Female Farmers |  |  | 0 |  |  |  | 1
| Female (Gen) |  |  | 0 |  |  |  | 1
| Female (OBC) |  |  | 0 |  |  |  | 0
| Female (SC) |  |  | 0 |  |  |  | 0
| Female (ST) |  |  | 0 |  |  |  | 0
| Female (Minorities) |  |  | 0 |  |  |  | 0
| Duration of training (in Days) |  |  | 1 |  |  |  | 2
| c) Within-District Training | 2514 | 10.06 | 1788 | 2.7708 | 1750 | 2.6577 | 3538 | 5.4285 | 54
(i)Within District (Residential)
| No. of Trainings Programmes * |  |  |  |  | 12 |  | 13
| No.of Participants * |  |  | 1788 |  | 1750 |  | 3538
| No of Male Farmers* |  |  | 1234 |  | 1138 |  | 2372
| Male (Gen) |  |  | 280 |  | 240 |  | 520
| Male (OBC) |  |  | 551 |  | 601 |  | 1152
| Male (SC) |  |  | 251 |  | 198 |  | 449
| Male (ST) |  |  | 100 |  | 55 |  | 155
| Male (Minorities) |  |  | 52 |  | 44 |  | 96
| No.of Female Farmers |  |  | 554 |  | 612 |  | 1166
| Female (Gen) |  |  | 65 |  | 55 |  | 120
| Female (OBC) |  |  | 369 |  | 349 |  | 718
| Female (SC) |  |  | 92 |  | 122 |  | 214
| Female (ST) |  |  | 28 |  | 73 |  | 101
| Female (Minorities) |  |  | 0 |  | 13 |  | 13
| Duration of training (in Days) |  |  | 8 |  | 6 |  | 6
c) (ii)Within District (Non Residential)
No. of Trainings Programmes *
No.of Participants *
No of Male Farmers*
Male (Gen)
Male (OBC)
Male (SC)
Male (ST)
Male (Minorities)
No.of Female Farmers
Female (Gen)
Female (OBC)
Female (SC)
Female (ST)
Female (Minorities)
Duration of training (in Days)
Total (B2)
B.3 | Demonstration
| Agriculture (Nos.) | 110 | 4.4 | 33 | 0.99 | 0 | 0 | 33 | 0.99 | 22.5
No of Demonstrations *
No of Participants *
No of Male Farmers *
Male (Gen)
Male (OBC)
Male (SC)
Male (ST)
Male (Minorities)
No.of Female Farmers *
Male (Gen)
Male (OBC)
Male (SC)
Male (ST)
Male (Minorities)
| Allied Sectors (Nos.) | 66 | 2.64
(i) AHD&F
(ii) Horticulture
(iii) Sericulture
(iv) Poultry
(v) Fodder Production
(vi) Any Other (give specification)
No of Demonstrations *
No of Participants *
No.of CIG involved
No of Sub Activities
No.of Individual Farmers *
No of Male Farmers *
Male (Gen)
Male (OBC)
Male (SC)
Male (ST)
Male (Minorities)
No.of Female Farmers *
Female (Gen)
Female (OBC)
Female (SC)
Female (ST)
Female (Minorities)
Farmer to Farmer Technology Dissemination at Demonstration Plot
Total (B3)
B.4 | Exposure Visit
| a) Inter-state | 110 | 0.88
No. of Exposure Visit *
No.of Participants *
No of Male Farmers *
Male (Gen)
Male (OBC)
Male (SC)
Male (ST)
Male (Minorities)
No.of Female Farmers*
Female (Gen)
Female (OBC)
Female (SC)
Female (ST)
Female (Minorities)
Duration of training (in Days)
| b) Within-state | 660 | 2.64
No. of Exposure Visit *
No.of Participants *
No of Male Farmers *
Male (Gen)
Male (OBC)
Male (SC)
Male (ST)
Male (Minorities)
No.of Female Farmers *
Female (Gen)
Female (OBC)
Female (SC)
Female (ST)
Female (Minorities)
Duration of training (in Days)
| c) Within-District | 1650 | 4.95 | 575 | 1.09 |  |  | 575 | 1.09 | 22
| No. of Exposure Visit * |  |  | 1 |  |  |  | 2
| No.of Participants * |  |  | 292 |  |  |  | 575
| No of Male Farmers * |  |  | 197 |  |  |  | 385
| Male (Gen) |  |  | 38 |  |  |  | 83
| Male (OBC) |  |  | 98 |  |  |  | 190
| Male (SC) |  |  | 35 |  |  |  | 70
| Male (ST) |  |  | 17 |  |  |  | 24
| Male (Minorities) |  |  | 9 |  |  |  | 18
| No.of Female Farmers * |  |  | 95 |  |  |  | 190
| Female (Gen) |  |  | 19 |  |  |  | 24
| Female (OBC) |  |  | 57 |  |  |  | 120
| Female (SC) |  |  | 13 |  |  |  | 30
| Female (ST) |  |  | 3 |  |  |  | 8
| Female (Minorities) |  |  | 3 |  |  |  | 8
| Duration of training (in Days) |  |  | 1 |  |  |  | 2
Total (B4)
B.5 | Mobilization of Farmers Group
| a) Capacity Building, skill development and support services | 66 | 3.3
No. of Groups formed *
No of members benefitted *
| b) Seed Money/Revolving fund | 33 | 3.3
No of groups provided seed money
No of members benefitted
| c)Food Security Groups | 22 | 2.2
No. of Groups formed *
No of members benefitted *
B.6 | Rewards & Incentives – Best organized group representing different enterprises (5 groups)
B.7 | Farmers Award at Block level | 55 | 5.5
Farmers Award at District level
B.8 | District level exhibitions, Kisan Melas, fruits/ Vegetable shows No. of events | 2 | 4
No. of events
Total no. of visitors
No of visitors ( Male )
Male (Gen)
Male (OBC)
Male (SC)
Male (ST)
Male (Minorities)
No of visitors ( Female )
Female (Gen)
Female (OBC)
Female (SC)
Female (ST)
Female (Minorities)
B.9 | a)Number of leaflets made and distributed Number of advertisements made
No Activities *
| a) Information Dissemination through printed Leaflets etc. & local advertisements |  | 1.5 | 0 | 0.636 |  |  | 0 | 0.636 | 42
| b) Low cost publication |  | 1.54 | 0 | 0.1696 |  | 0.75398 | 0 | 0.92358 | 60
B.10 | Number of technology packages developed (CD) | 4 | 0.8
No Activities *
III. Agricultural Technology Refinement, Validation and Adoption
B.11 | a)Farmers Scientist Interactions at district level | 1 | 0.2
No.of interaction *
No.of farmers Participated *
No of individual farmers (Male) *
Male (Gen)
Male (OBC)
Male (SC)
Male (ST)
Male (Minorities)
No of individual farmers (Female) *
Female (Gen)
Female (OBC)
Female (SC)
Female (ST)
Female (Minorities)
| b) Designate expert support from KVK/ SAU at district level. | 12 | 0.24
| c)Joint Visit by Scientist & Extension Workers |  | 0.14
B.12 | Organization of field days and Kisan Gosthies | 22 | 3.3 | 11 | 1.65 |  |  | 11 | 1.65 | 50
| No. of FD/KG * |  |  | 11 |  |  |  | 11
| No.of farmers Participated * |  |  | 1180 |  |  |  | 1180
| No of Male Farmers * |  |  | 805 |  |  |  | 805
| Male (Gen) |  |  | 264 |  |  |  | 264
| Male (OBC) |  |  | 398 |  |  |  | 398
| Male (SC) |  |  | 65 |  |  |  | 65
| Male (ST) |  |  | 45 |  |  |  | 45
| Male (Minorities) |  |  | 33 |  |  |  | 33
| No.of Female Farmers * |  |  | 375 |  |  |  | 375
| Female (Gen) |  |  | 66 |  |  |  | 66
| Female (OBC) |  |  | 213 |  |  |  | 213
| Female (SC) |  |  | 65 |  |  |  | 65
| Female (ST) |  |  | 19 |  |  |  | 19
| Female (Minorities) |  |  | 12 |  |  |  | 12
B.13 | Assessment, refinement, validation and adoption of frontline technologies and other short term researchable issues through KVKs and other local research centres. | 1 | 0.5
B.14 | Establishment of ATMA like institutions Recurring
| TA/DA AND Operational expenses at district level |  | 7.8 | 0 | 0.47453 | 0 | 0.34857 |  | 0.8231 | 11
| Operational expenses at block level | 11 | 2.2 | 11 | 1.1 |  |  | 11 | 1.1 | 50
| Hiring of vehicles (POL) |  | 1.8 | 0 | 0.758 | 0 | 0.46 | 0 | 1.218 | 68
| Operational Expeces of DFAC Meeting |  | 0.15
| Operatioal Expences of BFAC Meeting |  | 0.825 | 11 | 0.825 |  |  | 11 | 0.825 | 100
Non - Recurring : Equipment
Non - Recurring : Civil Works and Re-furbishing of ATMA Office
B.15 | Farm School | 44 | 12.942 | 22 | 4.544 |  |  | 22 | 4.544 | 35.11
| No.of Farm schools set up (Agriculture) |  |  | 22
No. of Farm schools set up (Allied)
Agriculture
i.) AHD&F
ii) Horticulture
iii) Sericulture
iv) Poultry
v) Fodder Production
vi) Any Other (give specification)
D. | INNOVATIVE ACTIVITIES – DISTRICT LEVEL
D.1 | Support for district level Training Institutions | 1 | 1
D.2 | Setting up CRS
D.3 | Farmers Friend (One FF / 2 village)
E.1 | OTHER INNOVATIVE ACTIVITIES
E.2 | Innovative activities – District component | 11 | 2.2 | 11 | 0.5765 | 0 | 0 | 11 | 0.5765 | 26.2
F.1 | Display Board
F.2 | Pico/Ultra-Light Portable Portable projector | 22 | 4.4
F.3 | Productiion of low cost films
F.4 | Hand Held Devices | 33 | 4.95
F.5 | GPRS Charges |  | 1.65
G 1 | Specialist and Functionary Support
G 2 | District Level |  | 11.636 |  | 4.568 |  | 0.53135 |  | 5.0994 | 44
Specialist and Functionary Support (PD)
Specialist and Functionary Support (DY PD)
Specialist and Functionary Support Accountant-cum-clerk
Specialist and Functionary Support Computer Programmer/Data Entry Operator
G3 | Specialist Support at Block Level(BTM) | 6 | 17.424 | 6 | 5.6863 |  |  | 6 | 5.6863 | 33
| Operational Expenses for BTM | 6 | 4.356 | 6 | 1.6454 |  |  | 6 | 1.6454 | 33
| Specialist Support at Block Level(ATM) | 13 | 20.764 | 13 | 7.4118 |  |  | 13 | 7.4118 | 36
| Operational Expenses for ATM at Block level | 13 | 7.55 | 13 | 2.59 |  |  | 13 | 2.59 | 36
| TOTAL (B.1 to G3) |  | 164.337 |  | 37.8017 |  | 4.7516 |  | 42.5533
Percent Achievement (%)
Project Director ATMA, Banka